## Work Rate Table
IRRIGATION RESTORATION & DEVELOPMENT PROJECT
Sub-project Name: Bagat Sufla Canal
Construction Schedule
WORKS | Unit | Quantity | Rate / day | Duration | Value of | Construction Year - 1 (2020) |  |  |  | Construction Year - 2 (2021)
|  |  |  | (days) | Work ($) | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov
Slack Period
Contractor's Work
Mobilization to Site
Joint Survey & Start of Construction Activity
Site -1: wier and intake structure with 4 social structures
Ordinary Soil Excavation: | m³ | 50130.1796 | 10
Plain cement Concrete M10(1:3:6): | m³ | 621.764 | 2
Air-Entrained Plain Cement Concrete (PCC-M20): | m³ | 323.658 | 10
Air-Entrained Mass Concrete(M20): | m³ | 10972.4525 | 5
Air-Entrained Reinforced Cement Concrete M25 : | m³ | 4274.1438 | 10
Joint Preparation at each 15m: | m | 573.4
Compacted Backfilling: | m3 | 27741.3 | 0.5
Graded Gravel Filter: | m3 | 1088.048
Geotextile Filter: | m2 | 10118
Air-Entrained RCC Slabs (100X100X15)cm M25: | m3 | 1517.7 | 10
Mild Steel Radial Gate (Type B): | m2 | 6 | 2
MS Channel (10*5*0.6)cm: | m | 46
Hand Rail: | m2 | 27.8
Stone Sign Board: | Ls | 4
Site Restoration: | Ls | 4
Joint Survey at Completion of Works
Issuance of Completion Certificate
Defects Liability Period Start
Handingover of Sub-project to Community
Community Works
0
Monthly completion Cost ( USD) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
Cummulative Completion Cost (USD) | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
Cummulative Completion Progress (%) | [5 empty] | 0% | 4% | 10% | 20% | 23% | 47% | 67% | 82% | 93% |  |  |  | 97% | 100%
Minimum Construction Equipment Required by Contractor |  | 1- Dumpy Level with staff and accessories (1nrs)
2- Concrete mixture (1nrs)
3- Concrete Vibrator (1nrs)
4- tractor trolly (1nrs)
5- Slump test equipment & concrete cubes
6- Coarse Aggregate cleaning Sieve
7- Aggregate boxes for concreteing (3nos)
8- Formwork as per requirements

## Resource Table
RESOURCE REQUIREMENT
Excavation in dry / wet natural ground |  |  | Quantity | = | 700 | m³
Required rate per day | = | 10 m³/day | Labour | = | 5 nrs labour will be required for 150 days
Excavation capacity of an Excavator | = | 120 m³/ day (0.5m³ buckect capacity) | OR, Excavator | = | 1nrs excavator for 40days
Excavation capacity of a labour | = | 2m³/day | Surveyor with helper & Equipment will be required
Laying Gabion Baskets |  |  | Quantity | = | 400 | m³
Required rate per day | = | 10 m³/day | Surveyor with helper & Equipment
Capacity of Tractor with trailer | = | 3.5m³/trip(say 3 trips/day) | Labour | = | 10 nrs labour will be required for 40 days
Loading / unloading labour | = | 32hrs/day | Stone | = | 10.5m³/day
Capacity of Gabion placing/filling labour | = | 2 m³/day
Placing Mass concrete with 20% Plum |  |  | Quantity | = | 550 | m³
Required rate per day | = | 10 m³/day | Surveyor with helper & equipment
Capacity of One Full Cement bag mixer machine | = | 13 m³/day(6hrs/day concerting) | Labours | = | 10 nrs for 55 days
Mason requirement | = | 8hrs/day | Tractor to shift stones
Labour for loading mixer machine | = | 64hrs/day
RESOURCE TOTAL
A: Manpower | B: Essential Equipments
Labour = 15 nos | Tractor with trailer = 1nos
Survey Team = 1nos | Plate compactor = 1nos
Tractor operator = 1nos | Level with staff guage = 1nos
Excavator Operator = 1nos (may require) | FDT appratus = 1nos
Mason = 2nos | Mixer Machine = 2nos
Mixer Operator = 1nos | Concrete Vibrator = 2nos
Site Engineer | Excavator = 1nos (may require)
Foreman / Supervisor